## Slide 1
Spiritual California
Marketplace Platform
Technical Project Plan & Estimates

## Slide 2
Executive Summary
Trust
Discovery
Commerce
Community
Monetization
Timeline: 28–31 weeks (~7–8 months)
Resource: 1 Senior Full Stack Dev + Claude AI Copilot
Confidence: 88–92% | MVP Go-Live: Week 24
Key Metrics
• 2 primary user roles (Seeker, Guide)
• 4 commerce verticals
• 1 AI feature (Journey Guide)
• Phase 2 ready (Subscriptions)

## Slide 3
Platform Differentiation
Trust
Identity + credential verification for all Guides
Discovery
AI-powered chatbot + robust search/filter
Commerce
End-to-end booking, events, and e-commerce
Community
Reviews, testimonials, practitioner blogs
Monetization
Stripe Connect + 12-20% commission

## Slide 4
Technology Stack
Frontend
Next.js 15 (App Router) + Vercel
Backend
NestJS 11 + Prisma 5.x
Database
PostgreSQL 16 + Redis 7
Search
Algolia v4
Storage
AWS S3 + CloudFront CDN
Payments
Stripe Connect
AI
Claude API (Sonnet 4.6)

## Slide 5
System Architecture
CLIENT LAYER
Next.js 15 | Mobile Web | Admin Panel
API LAYER
NestJS 11 (REST) | Auth | Services | Payments | AI
DATA LAYER
PostgreSQL | Redis | S3 | Algolia | BullMQ

## Slide 6
Development Phases
P1
Weeks 0-5
Infrastructure & Auth
P2
Weeks 6-10
User Onboarding & Verification
P3
Weeks 11-17
Marketplace Core Features
P4
Weeks 18-24
MVP Go-Live (Core Flows)
P5
Weeks 25-31
Advanced Features & Scale
Week 0 ──────────────────── Week 31
MVP Go-Live: Week 24

## Slide 7
Core Feature Modules
User Management (Seekers, Guides, Admins)
Verification & KYC (Persona + Document OCR)
Practitioner Profiles & Discovery
AI Journey Guide Chatbot
Booking & Calendar System
Payment Processing & Payouts (Stripe Connect)
Events & Soul Travels
Digital Products E-commerce
Reviews & Ratings System
Admin Dashboard & Analytics

## Slide 8
Effort Estimation
28-31
Weeks Total
160+
Dev Days
30-35%
AI Copilot Boost
88-92%
Confidence Level
Key Assumptions
• 1 dedicated Senior Full Stack Developer
• AI Copilot (Claude) integrated for full lifecycle
• No significant scope creep mid-project
• Third-party integrations work as expected
• Team communication is high-bandwidth

## Slide 9
Third-Party Integrations
Stripe Connect
HIGH
3-4 days
Persona (ID Verify)
HIGH
2-3 days
AWS Textract (OCR)
MEDIUM
1-2 days
Claude API (AI)
MEDIUM
1 days
Algolia (Search)
MEDIUM
1-2 days
Zoom SDK
HIGH
2-3 days

## Slide 10
Risk Register & Mitigation
API Integration Complexity
Spike 1 day early; have Stripe Identity as backup
AI Document Analysis Accuracy
Manual review fallback; iterative tuning
Web Scraper Anti-Bot Blocks
Stealth mode; respect robots.txt
Scope Creep Mid-Build
Strict change control; backlog for new features

## Slide 11
Milestone Timeline
M1
Week 5
M2
Week 10
M3
Week 17
M4
Week 24
M9
Week 35
Core Focus by Milestone
• M1-M2: Infrastructure, Auth, User onboarding & verification
• M3: Services, bookings, payments integrated
• M4: MVP ready — core flows tested
• M5-M9: Advanced features, events, products, subscriptions

## Slide 12
Infrastructure & DevOps
Local
Docker Compose
Staging
Railway (shared)
Production
Railway → AWS ECS
CI/CD Pipeline
→ Pull Request: Lint, typecheck, unit tests, build
→ Merge to main: All above + integration tests + deploy to staging
→ Tag release: Deploy to production + smoke tests + Sentry release
Cost Estimation
Phase 1 (0-10k users): ~$50-100/month (Railway)
Phase 2 (10k-100k users): ~$300-800/month (AWS)

## Slide 13
Definition of Done & Quality Gates
Per-Feature
✓ Peer-reviewed
✓ ≥80% test coverage
✓ Documented in Swagger
✓ No TypeScript any
✓ Input validated
Per-Phase
✓ Staged testing
✓ Regression tests pass
✓ No P0/P1 bugs
✓ Performance verified
✓ LCP < 2.5s
Production Go-Live Checklist
✓ All E2E tests green | Stripe Live mode | Sentry live
✓ Database backups verified | Rate limiting active | SSL valid
✓ Admin dashboard ready | 5+ Guides onboarded | Full flow tested

## Slide 14
Key Success Factors
1
AI-Powered Copilot
30-35% productivity boost on boilerplate & integration code
2
Robust Verification
Trust-first approach with Persona + Textract + Manual review
3
Efficient Tech Stack
Type-safe end-to-end (TypeScript, Prisma, Zod validation)
4
Clear Governance
Strict change control prevents scope creep mid-project
5
Monitoring from Day 1
Sentry + GitHub Actions CI/CD ensure quality at every step

## Slide 15
Next Steps & Approval
1
Week 1: Sign off on tech stack & architecture
2
Week 2-3: Finalize Figma wireframes with design team
3
Week 4: Set up repositories, CI/CD, & infrastructure
4
Week 5: Begin Phase 1 (Infrastructure & Auth)
Questions?
Technical Project Manager (Claude AI)
March 9, 2026